## Sheet1
GREEN ACTION PLAN
| PEOPLE |  | Position in 2022 | 2023 | 2024 | 2025
| GOALS | ACTIONS
1 | We have established a team of Green Leaders, including at Board level, who will lead us in the drive towards climate adaptation and instil a culture of shared responsibility across the organisation. | Meet monthly to review and update Green Plan (GP) and Green Action Plan (GAP) and to report to Board each quarter. Recruit 2nd Board member to sit on Green team. | GT established Nov 2017 Board Member recruited Dec 2018 | x | x | x
|  | Scope out available funding for a Sustainability Manager to lead on Green Plan. |  |  | x
2 | We are developing a programme of learning and education including workshops, talks, and events for everyone who works with us to develop an understanding of the issues arising from climate change and to support them on our journey. | Establish resources for staff available online and at Rockvilla including Green Libray, teams chat room for sharing resources and events. Ensure GT has representation from all depts across the company. |  | x
|  | Produce regular quarterly newsletter reporting on progress of green team and TGB activity for staff and Board |  | x
c | We will champion the use of Carbon Literacy Training throughout the sector to foster an awareness of the urgency of the climate crisis and contribute to a motivational shift in our response. | Include other organisations and freelancers we work with in our ongoing CLT and scope out the possibility of local trainers to reduce costs and increase capacity | 90% staff trained inc Board champion by 2022 |  | x
|  | Increase CLT for Board members to 50% |  |  | x
4 | We will be a centre for the exchange of skills, ideas and knowledge and use our learning to help promote climate literacy among everyone we interact with as we go forward | Host a platform of Production staff working in theatre in Scotland to ensure we work to the same standards and meet regularly to share expertise and ideas. |  | x
|  | Work with the Envelope Room and others to deliver workshops and talks for designers and others to promote the Theatre Green Book standards. |  | x
5 | We will communicate our actions, ambitions and commitments around climate adaptation and mitigation to our audiences and to the wider community | Update and publish Green Plan on website. Create GP Comms Strategy for Audiences around ongoing delivery and updating of GP. Action plan to be published on website | Original Green Plan published on website 2020 | x | x
|  | Develop a programme of audience education to include information on websites such as producton green info, interactive info in foyers and on our comms materials informing our audiences of our own journey | interactive set plans published on website 2022 |  | x
| PRODUCTION |  | Position in 2022 | 2023 | 2024 | 2025
| GOALS | ACTIONS
1 | We are committed to delivering work in line with the Theatre Green Book (Link here). This new guidance sets a common standard for a sustainable production process. From 2023 we will run all our productions and events according to the Intermediate standards. We will aim to reach Advance standards in production by 2025 | Together with the wider UK sector we shall ensure the future of the Theatre Green Book and work with sector organisations such as ABTT/SOLT/UK theatres trust to guarentee it remains relevant and vital |  |  | x
|  | Follow TGB intermediate guidance on all productions. Use TGB materials inventories for all events and productions to ensure our progress can be monitored and regularly audited | 70% of productions were run according to TGB intermediate standards in 2022 | x
2 | We will embed sustainability clauses in contracts with venues, companies, and individuals so that our principles are clear | Ensure all freelance staff have "green" clauses in their contracts. | Theatre Green Book intermediate clause in designers contracts 2021 | x
|  | Embed green clauses in our co production agreements and in all contracts with venues and partners |  |  | x
3 | We will work with all our artists and creative staff to support them throughout our sustainable production process and ensure that we collaborate, viewing this evolution in theatre practice as a positive creative opportunity | Develop clear guidance for all departments to include materials resources and sustainable practices and ensure they stay relevant and up to date | Costume guidance developed in 2022. | x | x
4 | We will reuse, repurpose, and recycle materials and employ a zero-to-landfil policy. We will always consider the life cycle of materials and equipment and aim to buy from local and sustainable sources | In partnership with Centrline scope out and secure funding to develop resource sharing software which can be used throughout the sector |  |  | x
|  | Rearrange existing storage space to allow for efficient repurposing of old sets into easily usable materials and ensure any unuseable materials do not end up in landfil. |  | x
| PROGRAMME |  | Position in 2022 | 2023 | 2024 | 2025
| GOALS | ACTIONS
1 | We will employ the talents and harness the ideas of Scotland’s artists to create bold productions that explore the climate crisis and address climate justice through compelling, optimistic storytelling that spurs action and creates hope for the future. | Ensure a minimum of 2 climate focused projects are in development each year. |  | x | x | x
|  | Over the course of the new strategic framework we will produce a minumum of three climate focused productions |  | x | x | x
|  | Climate change subject matter will be a priority criteria for all Theatre in Schools open calls and programme decision making |  | x | x | x
2 | We will work with arts and climate change partners to co-produce and present work to a broad audience across Scotland | Explore a partnership with Edinburgh Science Festival |  |  | x
3 | We will explore digital partnerships and opportunities to create work for an international audience | We will commission a minimum of 1 digital short focused on climate every two years |  | x | x | x
4 | we will ensure that the climate emergency is a focus of discussion and creative exchange within our artists development and creative engagement programmes | We will host a climate focused ideas generating event for artists |  | x | x
|  | We will ensure the climate is a key priority in any open calls for artistic residencies |  | x | x | x
| PLACES |  | Position in 2022 | 2023 | 2024 | 2025
| GOALS | ACTIONS
1 | We commit to reducing the carbon emissions from Rockvilla in line with government policy, but with the expectation that we can do better. | NTS is committed to running its business according to the guidance of the Theatre Green Book. We will ensure our building and operations run according to the guidance of book 2 (Sustainable buildings) and book 3 (Sustainable operations) |  |  | x
|  | Monitor carbon footprint of energy use in the building and continue to find ways to reduce ie switch off programmes, tight monitoring of the BMS and staff awareness. |  | x | x | x
2 | We will install a solar panel system on our roof at Rockvilla and intend to generate all our own electricity | Apply to electricity grid, secure funding and complete solar panel installation at Rockvilla | Initial 12kw system installed August 2021. |  | x
3 | We will ensure that our building is working hard to adapt and achieve its full sustainable potential, utilising new technologies. | Secure funding and install EV charging points at Rockvilla to allow staff to invest in their own cars |  |  | x
|  | Building management system updated to ensure ability to adapt energy use according to the use of the building |  | x
4 | In the course of our work outside our own building, we will engage with venues and sites throughout Scotland and beyond. We commit to ensuring that we do not have a negative environmental impact on the spaces and places we visit. | Develop green riders which can inform our stakeholders of the way we hope to work in their building |  | x
|  | Undertake environment risk assessments when working on site specific prodjects which take into account the existing environment and how we will protect it during the production |  |  | x
| PARTNERSHIPS |  | Position in 2022 | 2023 | 2024 | 2025
| GOALS | ACTIONS
1 | We will work collaboratively with our creative partners - co-producers, venues and communities - to ensure that our joint ventures adhere to The Theatre Green Book and that we share and gain learning that will influence all future work. | Working with National Theatre and National Theatre Wales we will devise a production aimed at highlighting new forms of sustainable theatre |  |  | x
2 | We will ensure that we share our learining with a wide range of organisations, stakeholders, individuals and government bodies, to grow our reach and influence across the country.
2 | We seek out partnerships with other organisations that can support us in our learning and ambitions, and aim to work with companies and individuals that share our commitment to a sustainable future. | Ensure that NTS plays an integral part in the future of the Theatre Green Book. Along with other national theatres scope out a model for management of the organisation to secure its future and be part of the organisation going forward. |  | x | x | x
3 | For those who are at an early stage in their learning and profession we will share our knowledge and commitment with them to build awareness and embed this thinking at a grassroots level. | Develop relationships within educational establishment to ensure that sustainability becomes a vital part of the training in drama and production skills. |  | x
|  | Develop our schools production skills workshop model to include sustainability. |  |  | x
| PROCUREMENT |  | Position in 2022 | 2023 | 2024 | 2025
| GOALS | ACTIONS
1 | We seek jointly to create sustainable value with our suppliers and favour those adopting a proactive approach towards minimising environmental impacts. | Develop and publish an aggressive procurement policy |  |  | x
2 | We will review our financial products and providers to ensure they work both for our people, our company and contribute to a more equitable and sustainable world. | Employ an ethical financial advisor to ensure we get the best advice with ethical financial products |  | x
|  | We will provide an ethical, green pension as a default for our staff |  | x
3 | We will strive to ensure that all products and materials used at Rockvilla and in our wider operations comes from equitable and sustainable sources or are reused, repurposed or recycled. | We commit to Rockvilla becoming a single-use plastic free building. We will source alternatives for production products that contain plastics ie gaffa tape/dance floor tape. | we have phased out the use of single use plastic from our offices and rehearsal spaces in 2022 |  | x
| MONITORING AND AUDITING |  | Position in 2022 | 2023 | 2024 | 2025
| GOALS | ACTIONS
1 | Our Action Plan will be regularly reviewed and evaluated by the Executive, Management, Staff and Board teams. | Quarterly reports from GT included in board papers. GT to discuss action plan by department at every GT meeting (monthly). Include TGB results. |  | x | x | x
|  | Website users encouraged to comment on GP and GAP through email. | email address for comments added to GP 2021 | x | x | x
2 | We will continue to find the most sustainable ways to tackle climate change and to hold ourselves to account. | GT to discuss new initiatives such as the Theatre Green Book and ensure that we keep up to date with the latest sector guidance |  | x | x | x
|  | Continue to be part of networking groups and encourage staff to attend conferences and training events outside the company |  | x | x | x